## Workplan
Workplan
Organisation Name:
Project Title:
Project Duration:
|  | MONTH-1 |  |  |  | MONTH-2 |  |  |  | MONTH-3 |  |  |  | MONTH-4 |  |  |  | MONTH-5 |  |  |  | MONTH-6
Activities and Tasks | Responsibility (Designation of Person In-charge) | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4

## Sample Workplan (hidden)
Workplan |  | List of activities and tasks with period of implementation highlighted. Use the same activity numbers and names as in the project description and budget.
Organisation Name: |  | Interactive Research and Development (IRD - Pakistan)
Project Title: |  | electronic Integrated Management of Childhood Illnesses - eIMCI
Project Duration: |  | Start Date: 1 Mar 2015 End Date: 15 Dec 2015 Months: 9.5
|  | YEAR 1 | [11 empty] | YEAR 2
Activities and Tasks | Responsibility (Designation of Person In-charge) | M1 | M1 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22 | M23 | M24
Activity 1. Project Resource Mobilization Activities
1.1 Setup of project and field Office | Project Manager
1.2 Hiring of project staff from local community | Project Manager /HR Manager
1.3 Meetings with government officials to introduce project. Including EDO Muzaffargarh, Representative of CMAM amd IYFC | Project Manager
1.4 Project Technical Advisory Committee Meeting | Project Director
Activity 2. Baseline Study
2.1 Development of survey tools, pretesting and finalization
2.2 Formulation of Survey teams
2.3 Data collection
2.4 Monitoring and surpervision
2.5 Data Validation, entry and cleaning
2.6 Data Analysis
2.7 Draft and final reports
Activity 3: eIMCI Tool Development | bar: YEAR 1 M1 to YEAR 1 M4
3.1 Requirements gathering workshop
3.2 Design and Development | bar: YEAR 1 M1 to YEAR 1 M4
3.3 Testing | bar: YEAR 1 M1 to YEAR 1 M4
3.4 Database setup and Installation | bar: YEAR 1 M4
3.5 Application setup on Tablets | bar: YEAR 1 M4
Activity 4: CHWs Training | bar: YEAR 1 M4
4.1 Staff classroom training on IMCI guidelines | bar: YEAR 1 M4
4.2 Staff classroom training on eIMCI | bar: YEAR 1 M4
4.3 Staff hands*on field training on eIMCI | bar: YEAR 1 M4
Activity 5: Target Population enrollment and follow up | bar: YEAR 1 M5 to YEAR 1 M9
Activity 6: Endline study | bar: YEAR 1 M9
6.1 Formulation of Survey teams | bar: YEAR 1 M9
6.2 Data collection | bar: YEAR 1 M9
6.3 Monitoring and surpervision | bar: YEAR 1 M9
6.4 Data Validation, entry and cleaning | bar: YEAR 1 M9
6.5 Focus groups - CHWs | bar: YEAR 1 M9
6.6 Focus groups - Parents | bar: YEAR 1 M9
6.7 Data Analysis | bar: YEAR 1 M9
6.8 Final reports | bar: YEAR 1 M9
Activity 7: Final Report Writing | bar: YEAR 1 M9 to YEAR 1 M10
7.1 Data Analysis | bar: YEAR 1 M9 to YEAR 1 M10
7.2 Final Report Writing | bar: YEAR 1 M9 to YEAR 1 M10
7.3 Result Dissemination | bar: YEAR 1 M9 to YEAR 1 M10