## Sheet1
Proposed Timeline: Final Evaluation
Project Title: Eye Care system integration project in Afghanistan
SN | Activities | Sub-tasks | Responsibility |  |  | Status | 2019
|  |  | Lead Role | Support | Review and Finalization |  | Q3 |  |  |  | Q4
[7 empty] | September |  |  |  | October |  |  |  | November |  |  |  | December
[7 empty] | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
1 | Pre-Award Requirements | Final evaluation ToRs preparation, reivew and finalization | FHF SAME/ HN | FHF M&E | FHF | in progress | bar: September 1
|  | EOI announcement by partner organization HealthNet TPO | FHF SAME/ HN | FHF M&E | FHF | TBD | bar: September 2
|  | Development of selection criterion and evaluation template to review evaluation proposals | FHF SAME/ HN | FHF M&E | FHF | TBD | bar: September 2
|  | Collection and review of Evaluation proposals | FHF SAME/ HN | FHF M&E | FHF | TBD | bar: September 3 to September 4
|  | Interview and selection of Evaluation consultant/ consulting firm to undertake mid-term evaluation as per FHF agreed criteria | FHF SAME/ HN | FHF M&E | FHF | TBD | bar: October 1
|  | Pre-award assessment and signing of contract as per FHF contract agreement | FHF SAME/ HN | FHF M&E | FHF | TBD | bar: October 1
2 | Inception Phase | Collection and review of project documents | Consultant | HN | FHF | TBD | bar: October 2
|  | Mapping of documents and stakeholders | Consultant | HN | FHF | TBD | bar: October 2
|  | Desk Review of documents | Consultant | HN | FHF | TBD | bar: October 2
|  | Finalize methodology and work plan and submit to HN and FHF | Consultant | HN | FHF | TBD | bar: October 2 to October 3
|  | FHF review and finalize project methodology and work plan | Consultant | HN | FHF | TBD | bar: October 1; October 4
|  | Development of evaluation tools in consultation with HN and FHF | Consultant | HN | FHF | TBD | bar: October 4
|  | Evaluation tools finalized | Consultant | HN | FHF | TBD | bar: October 4
|  | Translation of evaluation tools | Consultant | HN | FHF | TBD | bar: October 4
|  | Submission of Protocol to IRB | Consultant | HN | FHF | TBD | bar: October 3
|  | Preparation of inception report | Consultant | HN | FHF | TBD | bar: October 4
|  | Share inception report | Consultant | HN | FHF | TBD | bar: November 1
|  | Finalize inception phase | Consultant | HN | FHF | TBD | bar: November 1 to November 2
|  | Recruitment and training of field team | Consultant | HN | FHF | TBD | bar: November 2
3 | Training of Field teams | Adaptation of training materials | Consultant | HN | FHF | TBD | bar: November 2 to November 3
|  | Preparation of final training schedule | Consultant | HN | FHF | TBD | bar: November 3
|  | Organization of training | Consultant | HN | FHF | TBD | bar: November 3
4 | Team Deployment | Deployment of study teams to provinces | Consultant | HN | FHF | TBD | bar: November 4 to December 3
|  | Coordinate study plan with provincial teams | Consultant | HN | FHF | TBD | bar: November 4 to December 3
|  | Schedule interviews at school and other settings | Consultant | HN | FHF | TBD | bar: November 4 to December 3
5 | Data Collection | Conduct interviews at schools with staff only and HN staff members | Consultant | HN | FHF | TBD | bar: November 4 to December 3
|  | Exit interview with sample of trained teachers and HN staff members | Consultant | HN | FHF | TBD | bar: November 4 to December 3
|  | Direct observation of facilities and UEH hospitals | Consultant | HN | FHF | TBD | bar: November 4 to December 3
|  | Quality assurance & monitoring of data | Consultant | HN | FHF | TBD | bar: November 4 to December 3
6 | Data Analysis | Transcription of field notes | Consultant | HN | FHF | TBD | bar: December 1 to December 2
|  | Identifying themes and subthemes | Consultant | HN | FHF | TBD | bar: December 1 to December 2
|  | Analysis of qualitative and quantitative data | Consultant | HN | FHF | TBD | bar: December 1 to December 2
|  | Submission of data analysis report to HN and FHF | Consultant | HN | FHF | TBD | bar: December 1 to December 2
|  | FHF review and share feedback | Consultant | HN | FHF | TBD | bar: December 2
7 | Final Report | Organize information | Consultant | HN | FHF | TBD | bar: December 2
|  | Submission of first draft of report | Consultant | HN | FHF | TBD | bar: December 3
|  | FHF review and share feedback on draft report | Consultant | HN | FHF | TBD | bar: December 3
|  | Final submission and project close out | Consultant | HN | FHF | TBD | bar: December 3
skype call with FHF/HN team
skype call with FHF/HN and FHF M&E team